# Steering Committee Call – 6/21/17

| Location: | Webex Conference Call (see below) | Leader: | Donald Edmondson |
| --- | --- | --- | --- |
| Date: | 6/21/17 | Note Taker: | Laura Meli |
| Attendees: | Aron Marquitz, Chandra Keller-Allen, Danielle Mitnick, Dave Almeida, Donald Edmondson, Eric Loucks, Karina Davidson, Jeffrey Birk, Janine Simmons, Jon King, Kate Stoney, Josh Smyth, Luis Tully, Mary Perry, Matthew Sacchet, Melissa Riddle, Stephen Metcalf, Will Aklin, Lisa Onken, Wendy Weber, Rosalind King, Becky Acabchuk, Alison Miller, Laura Meli, Lilly Derby (Note: additional call-in attendees were present) |  |  |
| Time: | 2pm EST |  |  |
| Meeting URL: https://meetings.webex.com/collabs/#/meetings/joinbynumber Meeting Number: 192 013 768 If using phone line for audio/teleconferencing: +1-415-655-0001 and enter the meeting number, once prompted If using audio from your computer: Once you join the meeting, select “Call Using Computer” to automatically connect |  |  |  |

| ACTION ITEMS FROM PREVIOUS MEETING | Responsible | Status |
| --- | --- | --- |
| RSVP on website or contact Laura ASAP if interested in Stress Retreat | Steering Committee | IN PROGRESS |
| Create OSF account and email Laura to confirm/have her add you to project page | UH2 PIs | IN PROGRESS |
| Create OSF account & reach out to RCC for next steps | UH2s | IN PROGRESS |

| AGENDA ITEMS | Presenter |
| --- | --- |
| - Website - Measures Repository - Internal Site - External Site | RCC, NIH, UH2 |
| MEASURES REPOSITORY - The RCC has developed a platform for submitting Measures via the internal website. Attached to the minutes is a video tutorial explaining how to use the system, which includes information regarding the review process. - Process: Once a UH2 team submits a measure, the RCC will assign a primary and secondary reviewer from the Protocol & Technical Guidelines Subcommittee to take a look at the materials you submitted and ensure that they follow SOBC guidelines. The rest of the subcommittee is also welcome to comment. Review will take place on the Protocol & Technical Guidelines Subcommittee discussion board. Once reviewed, the RCC will collate and notify the UH2 team. The UH2 team will be made aware of any feedback via the discussion board and the team will have the chance to revise and resubmit. Once finalized and approved, the measure will be publically available on the Measures Repository. - UH2 teams noted a handful of changes requested for the form (i.e. including other options for computerized/paper, clarifying language relating to the validation steps). - The Marsch/Poldrack and Loucks/Britton/King groups have been awarded in-Network supplements relating to the posting of assays and will be submitting roughly 50 measures in the coming weeks. Other teams should prepare to submit the first of their measures this summer. Measures do not need to be fully validated in order to submit; it is acceptable to submit a measure that is only in the first stage, Identified, and later amend the measure. - NYU submitted the first measures early in June. Danielle Mitnick (NYU) provided positive feedback regarding the process and functionality. She noted that RCC is receptive to questions and to include screenshots when possible to help clarify technical issues/questions. There are some bugs, but RCC/developers are able to help resolve quickly. Feedback: - Option to add a PMCID instead of manuscript. Could there be copyright issues if are including papers that aren’t yet published? Jon King will verify what copyright issues we need to be aware of and circumnavigate. - RCC will amend any website content that uses the language “measure is measured” and change it to include a clear description of this step (i.e. the psychometric properties of the measure have been assessed for validity and reliability) - Add Jon King to the Protocol & Technical Guidelines Subcommittee - Down the line it may be of interest to include other behavior change outcomes (i.e. lipids). RCC may add an “Additional Evidence” box to the form later on INTERNAL/EXTERNAL SITE - The RCC reminded the network that the website is meant to serve the entire network. If there are ever materials, news, or discussions/questions, please feel free to post or request that the RCC post to either the internal or external site. - Please share the link on your social media and send it to your friends/colleagues in order to increase traffic and SEO. Google Analytics - Overall Visits– about 900 visits in total (30% new/70% returning) - Search Engine Optimization (SEO) – The website link is now up on the NIH SOBC site and RCC is looking into other creative ways to drive traffic to our website. |  |
| - Open Science Framework | RCC |
| - A few reminders have gone out to UH2 teams regarding OSF and how to make them publically accessible. This is high priority because OSF links are needed to submit measures. Please let the RCC know if you have any questions. Note: Between the time of this call and the circulation of meeting minutes, all teams have activated their OSF pages. All SOBC UH2s now have public pages on OSF searchable by PI name or SOBC project name. |  |
| - Cross-project Collaborations - Stress Retreat - Grand Rounds | RCC |
| - Stress Retreat – The NYC Stress Retreat is scheduled for Nov 9-10 in New York City hosted by the RCC and representatives from UCSF. The retreat will be highly personalized, so attendees must be confirmed early on (by July). - Current RSVPs: Alison Miller, Eric Loucks, Johannes Haushofer, Rick Heyman, Becky Ferrer. If anyone else would like to attend or sees that they have incorrectly been counted as attending, please notify the RCC. This month, the RCC will reaching out to attendees to discuss needs further. - Grand Rounds –All upcoming Grand Rounds are on the Events calendar in the website. Times and call information has been added and speaker info will be added as webinars are scheduled. Grand Rounds are public events; please invite anyone who may be interested and circulate announcements to colleagues, trainees, etc. - Scheduled speakers: September (MD2K), and November (Tessa West). July’s GR is cancelled due to conflicting conferences/summer vacations. |  |
| - Outreach Dissemination - Manuscript Updates - Conference Updates - Other Projects | UH2 PIs |
| MANUSCRIPT UPDATES NETWORK PAPERS - Special Issue–All papers are either being reviewed or revised. Revisions are due August 11 via the submission portal. Jennifer Sumner has reached out with details. There is currently a November 2017 publication date. - Identifying Target Mechanisms (Systematic Review) – The UConn team has drafted a proposal for a network-wide systematic review. This document was attached to the minutes and posted on the website. - The O/D Subcommittee reviewed and provided some helpful feedback. - This proposal is now posted for SC review on the website. Please comment with any thoughts/feedback during the 2 -week review window. - Systematic Review Core - Some UH2 teams are currently working with Becky/Blair at UConn or have reached out with questions, but a reminder that the RCC does have a team at UConn of meta-analysis/systematic review experts ready to consult/support with any questions, projects, etc. RCC PAPERS - Adherence Measures White Paper – Ian Kronish is developing a best practices paper for adherence measures and wants to do so in conjunction with the SOBC network/optimize the manuscript for SOBC researchers. Please provide any feedback/thoughts on the discussion post. Manuscript in progress. - Physical Activity & Mechanisms (Systematic Review) – RCC is working on a systematic review of all NIH funded studies that measured mechanisms relating to physical activity as an outcome. Currently drafting the Prospero Protocol and doing preliminary searches. CONFERENCE UPDATES - APS Boston – The SOBC workshop at APS Boston received positive feedback. The excitement and engagement from junior researchers was clear. Materials form the conference are posted on the Resources page of the external site. OTHER PROJECTS - SOBC Newsletter- The RCC is putting together a newsletter to keep in touch with contacts and share news with colleagues. If any network members have job postings, interesting articles, content you’d like shared, please reach out to the RCC. The first newsletter will go out in July. Please forward along to anyone who may be interested. |  |
| - Other Updates - Good Clinical Practices | RCC, NIH, UH2 |
| - GCP – Melissa and her team are leading the GCP Workshop planned for July 6/7, 2017 in Bethesda, MD. There were a couple of webinars last week to help prepare for the meeting. Finalized agenda/materials/updated participant list will be out shortly from Melissa or Chandra. If anyone else is able to attend, please contact Chandra. - Please provide feedback on the BSR template materials/sections or places that might need additional attention from the perspective of a BSR. |  |
| - Wrap Up and Action Items | RCC |

| ACTION ITEMS | Responsible | Due Date |
| --- | --- | --- |
| - Provide feedback on GCP materials (to be received in email from Chandra/Melissa) | Steering Committee |  |
| - Send content, news, job postings, etc to RCC for SOBC Newsletter | Steering Committee |  |
| - Provide thoughts/feedback on Identify Target Mechanisms (Sys Review) proposal on website discussion thread | Steering Committee | July 5 |
| - Special Issue revisions | Special Issue participating authors | Aug 11 |
| - RSVP to NYC Stress Retreat | Steering Committee | August 2017 |
| - Prepare to submit measures via the internal website Measure Validation Form | UH2 Teams | Summer 2017 |

Attachments (if necessary)

- Measure Validation Form & Measures Repository Video Tutorial