# Steering Committee Call - 9/21/16

| Location: | 646-317-5469 | Leader: | Donald Edmondson |  |  |
| --- | --- | --- | --- | --- | --- |
| Date: | 9/21/16 | Note Taker: | Laura Meli |  |  |
| Time: | 2pm EST | Call In #: | 646-317-5469 | Code: |  |
| Attendees: | RCC: Donald Edmondson, Jen Sumner, Laura Meli UH2 Teams: Jun Ma, Russ Poldrack, Dave Almeida, Josh Smyth, Johannes Haushofer, Rick Heyman, Eric Loucks, Alison Miller NIH: Lis Nielsen, Jon King, Mary Perry, Elaine Collier, Melissa Riddle, Chandra Keller-Allen |  |  |  |  |

MEETING OBJECTIVES

- Revisit new call structures and subcommittee plan - Determine Steering Committee chair - Delegate subcommittee/develop action plan for SOBC Measures Rubric

| AGENDA ITEMS | Presenter |
| --- | --- |
| - General Updates - Steering Committee Call structure and Subcommittee plan - Steering Committee chair - Measures/Collaboration chart - Website transition | RCC |
| Discussion -New Steering Committee call structure will reflect this agenda – please email the RCC with any preferences/suggestions -RFA language states that Steering Committee chair can rotate based on vote after year 1 of grant -If you would like to nominate self/others, email RCC -RCC will continue as chair if receive no nominations -RCC compiling all measures to develop an online SOBC measure registry – please send edits if you haven’t done so -Plan to put up the measures that are being tested now, and eventually what has been validated/approved -RCC tracking all collaborations to help identify synergies/help trumpet SOBC mission -Protocol/Guidelines subcommittee will discuss development/implementation of SOBC Measure Rubric -Considerations: Is this an appropriate time? Would one metric suit all measures/studies (heterogeneity)? -Some UH2 groups voiced concerns re: confidence in posting measures at this stage -RCC is working to develop/launch a new external/internal SOBC website |  |
| - UH2 Updates (will begin next call) - Progress - Barriers - Next steps - Network resources/requests (subcommittees, RCC, cross-site consultations, collaborations, etc.) | UH2 PIs |
| Discussion -For the next call, RCC will reach out to two UH2 groups in advance to provide updates; please email RCC if you would like to provide updates on next call -Will be piloting video conference platform for Grand Rounds – hopefully use for Steering Committee calls |  |
| - Cross-project Collaborations - Update on existing collaborations - Pilot funds - Ideas for new collaborations | RCC |
| Discussion -Please email RCC with new/unlisted cross-project collaborations (within SOBC network) -RCC had pilot funds to assist with collaborations (add measures into projects, small meetings, embedded experiences across groups, pre-conference workshops, etc) -Slep/Heyman update: testing Qualtrics; about $5 per completed participant; seems easy to integrate -RCC working to develop guidelines/proposal process for pilot funds -Budget allows ~$25,000; money set aside for each budget year |  |
| - Outreach and Dissemination - Manuscripts - Conferences/presentations - Other/new projects | RCC |
| Discussion -Special Issue: March 1, 2017 submission portal opens for manuscripts; Lis, Jen, Ted are guest editors and available for questions -SOBC Overview papers (Marker/Viewpoint papers) will pilot corporate authorship -RCC will send proposed list for corporate authorship and request feedback/preferences -SOBC will present symposia at APS, SCRD, and SBM -RCC will circulate an Outreach/Dissemination update prior to each Steering Committee call -UH2’s to send RCC news of any investigator initiated programming/related presentations for tracking/to be included in updates -RCC pursuing other means of dissemination (podcasts, press packages for news sources, etc) -Email any relevant media contacts to RCC -Pursue a second Special Issue after data is available – potentially in Nature Human Behavior (new journal) -RCC looking into Survey Monkey collaboration to share measures |  |
| - Open Science and Data Sharing - Updates - Issues/concerns/needs - Next steps | RCC |
| Discussion -RCC is developing and piloting a system to transition UH2 teams to Open Science Framework; creating a handbook and will reach out to teams individually -Piloting at Columbia (conservative IRB) -RCC interviewing/meeting with Poldrack and Haushofer re: their experiences being open |  |
| - General Questions/Needs | UH2 PIs |
| Discussion |  |
| - Wrap Up and Action Items | RCC |
| Discussion -Grand Rounds 9/27– Elissa Epel and The NIA funded Stress Measurement Network; will be part guest lecture/part sandbox play -Piloting new video conferencing platform -This time, closed to Steering Committee; in the future will be open to others |  |

| ACTION ITEMS | Responsible | Due Date |
| --- | --- | --- |
| - Email RCC with any preferred changes/feedback re: new call structure | UH2 | 10/3/16 |
| - Email nominations for Steering Committee chair to RCC | UH2/NIH | 10/3/16 |
| - Email updated list of measures and new collaborations to Laura Meli | UH2 | 9/30/16 |
| - Send out Protocol/Guideline Subcommittee roster for UH2 review | RCC | 9/27/16 |
| - Email RCC to switch off of/join Protocol/Guidelines Subcommittee | UH2 | 9/30/16 |
| - Protocol/Guidelines Subcommittee activated: Discuss development/implementation of SOBC Measure Rubric | Protocol/Guidelines Subcommittee (RCC will email to initiate) | Ongoing (provide update on 10/19 call) |
| - Email RCC if you’d like to present updates on 10/19 call | UH2 | 10/5/16 |
| - Circulate details of Qualtrics | RCC and Heyman/Slep | 9/30/16 |
| - Send proposed list for corporate authorship | RCC | 9/30/16 |
| - Provide feedback on corporate authorship list to RCC | UH2 | 10/3/16 |

Attachments (if necessary)

- Updated Assay Chart and Collaboration List - Assay Rubric draft - Almeida/Smyth EMA Stress document - Outreach/Dissemination Log - Steering Committee Call Structure (monthly) - Grand Rounds Call Structure (bimonthly)