# Steering Committee Call – 8/16/17

| Location: | Webex Conference Call (see below) | Leader: | Donald Edmondson |
| --- | --- | --- | --- |
| Date: | 8/16/17 | Note Taker: | Emily Cea |
| Attendees: | Acabchuk, R., Almeida, D., Collier, E., Esopo, K., Hennessy, E., King, J., Ma, J., Miller, A. Mitnick, D., Poldrack, R., Smyth, J., Stoney, C., Whicker, C., Birk, J., Cea, E., Cornelius, T., Davidson, K., Edmondson, D. |  |  |
| Time: | 2pm EST |  |  |
| Meeting URL: https://meetings.webex.com/collabs/#/meetings/joinbynumber Meeting Number: 192 013 768 If using phone line for audio/teleconferencing: +1-415-655-0001 and enter the meeting number, once prompted If using audio from your computer: Once you join the meeting, select “Call Using Computer” to automatically connect |  |  |  |

| ACTION ITEMS FROM PREVIOUS MEETING | Responsible | Status |
| --- | --- | --- |
| First 23 of SOBC measures to be revised and published | Marsch/Poldrack/Loucks/Mitnick/RCC | COMPLETE |
| Send content, news, job postings, etc to RCC for SOBC Newsletter | Steering Committee | IN PROCESS |
| Circulate GCP Workshop meeting summary and recommendations | Chandra | IN PROCESS |
| Share Grand Rounds dates/times with colleagues/collaborators | Steering Committee | IN PROCESS |
| Send first SOBC newsletter | RCC | August 14, 2017 |
| Share preferred SOBC conferences with RCC | Steering Committee | August 2017 |
| Submit Special Issue revisions via submission portal | Steering Committee | August 11, 2017 |
| Continue submitting measures for review via the Measures Form on the internal website | UH2 Teams | Summer 2017 |
| Prepare to submit measures via the internal website Measure Validation Form | UH2 Teams | Summer 2017 |

| AGENDA ITEMS | Presenter |
| --- | --- |
| - General Updates/Housekeeping | RCC |
| - The RCC has had a recent personnel change – Laura Meli has now transitioned to a part-time role and Emily Cea has taken over her position within the RCC. - Feel free to contact Emily with any general matters, concerns, or questions. Laura will be managing the Measures Repository, so please continue to reach out to her directly with any needs or questions about this project. |  |
| - Website - Measures Repository - Internal/External Site | RCC, NIH, UH2 |
| MEASURES REPOSITORY - The tentative RCC timeline is for 70 measures published on the repository by August 23. Thank you to NYU, Loucks, and the Poldrack/Marsch teams for leading this initiative and working with the RCC to optimize the process. - The RCC is in the process of developing efficient internal systems to expedite the review process and ensure the sustainability and quality of the repository is intact. - Over the last month, the RCC has been working with the SOBC website developers to update some minor glitches in the repository before making the site public. Once they make the changes we’ve requested, the repository will be ready to go live. We’ll be sure to inform you when this happens so that you can share the link with your colleagues and networks. - The RCC is working on adding a field on the submission form and repository for a “Downloadable Measure & Instructions” so that users can use the repository as one-stop shopping. Please feel free to send these materials in any format that works for you to Laura. It will be a new field on the form shortly and the RCC will be retroactively requesting these materials from those who have already submitted their measures. - As always, please continue to let the RCC know of any preferred changes to the form or submission process. The RCC will work to update the site with those changes as they come up. INTERNAL/EXTERNAL SITE - As the RCC continues to improve the functionality and appearance of the website, the “About” page has been made into a drop-down menu including the “History,” “Network,” and “Partners” to make the content a bit more user-friendly. - The website’s Partners Page is now live and the RCC is welcoming suggestions of groups to help expand our reach. In addition to including society partnerships on this site, the RCC is also interested in building out another section of this page to include “Other Research Networks” (i.e., MD2K, the Stress Measurement Network, the Center for Open Science, etc). Please direct suggestions of groups we can partner with or groups that you are a part of and would like represented to Emily Cea. The RCC is appreciative of any and all suggestions. - The RCC has been posting relevant systematic reviews, publications, and news and events on the website. Feel free to check that out when you have a moment. - After producing a google analytics report looking at the overall traffic to the website, the RCC has learned a lot about who makes up the SOBC website audience. Over the past month, it appears that about two-thirds of our visitors are returning and that the average duration of each session spent on the site is close to 7 minutes. |  |
| - Cross-project Collaborations - Grand Rounds | RCC, NIH, UH2 |
| GRAND ROUNDS - The upcoming Grand Rounds presentation from MD2K’s Santosh Kumar will be Monday, September 25, 2017. The RCC is looking forward to this webinar and hopes that you will be able to join in. - As you may already know, all upcoming Grand Rounds (dates, times, call information) are on the SOBC Events calendar on the internal website. - As a reminder, Grand Rounds are public events. Please invite anyone who may be interested and circulate announcements to colleagues, trainees, and network members. As the RCC strategizes how to ensure these presentations get strong visibility, please let us know of any suggestions you might have to increase access and visibility. |  |
| - Outreach Dissemination - Manuscript Updates Network Papers - Special Issue - Identifying Target Mechanisms (Systematic Review) - Systematic Review Core RCC Papers - Adherence Measures White Paper - Conference Updates - 2018 Conference Ideas - Other Projects - Society Endorsements - SOBC Newsletter | RCC, NIH, UH2 |
| MANUSCRIPT UPDATES NETWORK PAPERS - Special Issue – All revisions have been submitted to the submission portal. A notification of acceptances should be made sometime in September 2017 and a publication date should be expected in December 2017. - Jen Sumner, Lis Nielsen, and Ted Beauchaine are in the process of developing an editorial introduction to the special issue as well. - Identifying Target Mechanisms (Systematic Review) – The UConn team is continuing to move forward with their network-wide systematic review. After discussing with them a couple weeks ago, the RCC is looking forward to seeing what progress they make in the upcoming months. - Systematic Review Core – As a reminder, the RCC works with the Systematic Review Core at UConn, which consists of experts in meta-analysis/systematic review. This team is ready to consult and support UH2’s with any questions, projects, etc. RCC PAPERS - Adherence Measures White Paper – Ian Kronish is still in the process of developing a best practices paper for adherence measures. This will be a strong network resource and may be helpful for the UH3 transition. - Ian will be available to give feedback on what measures you are using. Please reach out to him as you are thinking about UH3 transition, and consider sharing what adherence tools you are using. CONFERENCE UPDATES - As we mentioned last month, the RCC has started planning what conferences would be important for the network to attend in 2017/2018. Please below for a list of some those conferences and associated updates. - European Health Psychology Society 2017 (Aug 29-Sept 2, Padua, Italy) - Roundtable discussion with SOBC (Jen Sumner) and the Human Behavior Change Project (Susan Michie, Marie Johnston, Rachel Carey), highlighting unique features and synergy. - American Psychosomatic Society (APS) 2018 (March 7-10, Louisville, KY) - Preparing a symposium and roundtable lunch for submission. - Symposium will include an NIH overview and presentations of initial findings of UH2 projects from 2-3 teams (could include the RCC to provide rationale for SOBC). - Roundtable lunch will involve an introduction to the SOBC Measures Repository and a hands-on exercise. - Please let Jen and Emily know if your team is interested in participating in this symposium. - Society of Behavioral Medicine (SBM) 2018 (April 11-14, New Orleans, LA) - Currently preparing a symposium with the following presenters: Jun Ma, Josh Smyth, RCC presentation on SOBC Measures Repository, and Susan Czajkowski as discussant. - Society for Prevention Research (SPR) 2018 (May 29-June 1, Washington, DC) - SPR is interested in SOBC having a big presence at this conference. - Association for Psychological Science (APS) 2018 (May 24-27, San Francisco, CA) - International Congress of Behavioral Medicine (ICBM) 2018 (November 14-17, Las Condes, Chile) - The RCC is also interested in attending the Academy of Behavioral Medicine Research (ABMR) conference in South Carolina. RCC is currently working on getting involved in this as well. - Talea Cornelius, from the RCC, will be representing SOBC at the Obesity Society Meeting in November 2017. OTHER PROJECTS - Society Endorsements - The RCC is continuing to work on developing strong partnerships with prominent behavioral science and psychology societies in the coming months in order to further align SOBC with other groups and pre-existing networks. - After a very productive call with the Society of Behavioral Medicine (SBM) in late July, the RCC has been working on a few projects to help expand SOBC’s network reach and bring more viewers to our website. Some of those plans include crosslinking our websites through our partners page, featuring SOBC in an Outlook Newsletter article discussing the Measures Repository, and recruiting an SOBC representative and SBM member to join their consultation program and function as a liaison between the organizations. - The RCC is also planning to meet with the Association for Psychological Science (APS) toward the end of August to determine the best ways to partner (newsletter article, partners page blurb, etc). - Since the last Steering Committee call, The American Psychosomatic Society (APS) extended a formal partnership with SOBC. The RCC is working to get them up on the SOBC website in the near future. - While the RCC continues to build connections to societies like SBM, APS, APS, ABMR, SPR, etc., please feel free to reach out to inform us of any other societies and/or research networks that you think SOBC should feature on our partners page. - SOBC Newsletter – The SOBC newsletter looks great, and the RCC is looking forward to sharing it. This resource will allow the public and scientific communities to connect with us and share news with colleagues and collaborators. Please reach out to the RCC with job postings, interesting articles, and content you would like shared. The first newsletter will go out in mid-August with the Measure’s Repository announcement. |  |
| - Wrap Up and Action Items | RCC |
| - Please be aware of some upcoming dates and deadlines to keep in the back of your mind. - Live Measures Repository – By Friday, August 18, 2017 - Special Issue - Acceptance notifications – September 2017 - Publication date – December 2017 - September Grand Rounds Presentation with Santosh Kumar – September 25, 2017 - As a reminder, all dates are posted to the SOBC internal calendar. - Please keep an eye out for emails from Jennifer Sumner regarding SOBC conference submissions. |  |

| ACTION ITEMS | Responsible | Due Date |
| --- | --- | --- |
| - Reach out to Association for Psychological Science (APS) for partnership discussion | RCC | August 2017 |

Attachments (if necessary)

- Conference Spreadsheet (2017/2018)